## DPR-XXX
DAILY WORK PROGRESS REPORT
Location & Plan: |  |  | Gabon |  |  | Vessel: | Navigator Z
LATITUDE | 03-51 S | WIND (kn) | S 12 | TEMPERATURE | 23 | Date: | 26.06.2026
LONGITUDE | 010-32 E | SEA STATE | Moderate | CURRENT (speed & dir.) | VAR | Location / Field | ETAME Field
TRANSIT INFORMATION
Transit Route From / To | Distance (Nm) | Distance covered (Nm) | Average Speed (Kts) | Total Distance covered (Nm) | Total Average Speed (Kts) | Distance to go (Nm) | ETA
OPERATIONS (SES: sailing at eco speed, SFS: sailing at full speed, AHO: AH ops, SOP: Supply ops, TOP: Towing ops, IDP: Idle at port, IAS: Idle at sea)
SES | SFS | AHO | SOP | TOP | IDP | IAS | TOTAL HOURS (24)
10 | 0 | 0 | 14 | 0 | 0 | 0 | 24
HOURS ON DP (SES: sailing at eco speed, SFS: sailing at full speed, AHO: AH ops, SOP: Supply ops, TOP: Towing ops, IDP: Idle at port, IAS: Idle at sea)
SES | SFS | AHO | SOP | TOP | IDP | IAS | TOTAL HOURS ON DP
0 | 0 | 0 | 14 | 0 | 0 | 0 | 14
Fluid consumption / produced
Fluid type | Unit | Prev. Balance | Consumed / Produced | Bunk in | Bunk out | Balance | Comments
Fuel - MGO | m³ | 276.3 | 17.5 | 0 | 0 | 258.8
M/E Lub oil | L | 3000 | 0 | 0 | 0 | 3000 | 15W-40
A/E Lub oil | L | 0 | 0 | 0 | 0 | 0
Hydraulic oil | L | 200 | 0 | 0 | 0 | 200 | HVI Plus100
Gear Oil | L | 500 | 0 | 0 | 0 | 500 | Cladium 100
Fresh Water | m³ | 460 | 4 | 0 | 25 | 431
Mud | m³ | 0 | 0 | 0 | 0 | 0
Brine | m³ | 0 | 0 | 0 | 0 | 0
Cement | Tons | 0 | 0 | 0 | 0 | 0
Barite | Tons | 0 | 0 | 0 | 0 | 0
Bentonite | Tons | 0 | 0 | 0 | 0 | 0
Bilge Water | m³ | 2 | 0 | 0 | 0 | 2
Dirty Oil | m³ | 5 | 0 | 0 | 0 | 5
Sludges | m³ | 2 | 0 | 0 | 0 | 2
Sewage | m³ | 0 | 0 | 0 | 0 | 0
POB
POB NUMBER | POB - PREVIOUS 24H | IN | OUT | POB TOTAL @ 24H
CREW | 15 | 0 | 0 | 15
PASSENGER | 5 | 0 | 5 | 0
OTHER | 0 | 0 | 0 | 0
SUBTOTAL | 20 | 0 | 5 | 15
MACHINERY
|  | Run hours from last report | Monthly | Since last O/H | TOTAL R/H | Last Lube oil change | Next Lube oil change
Run hrs for Port ME |  | 24 | 562 | 13532 | 50678 | 50180 | 51380 (1200h) | 538 | 13508 | 50654
Run hrs for Stbd ME |  | 24 | 562 | 14463 | 48957 | 48440 | 49640 (1200h) | 538 | 14439 | 48933
Run hrs for generator No1 (P) |  | 0 | 86 | 8804 | 46022 | 45998 | 46398 (400h) | 86 | 8804 | 46022
Run hrs for generator No2 (S) |  | 24 | 621 | 7689 | 52967 | 52730 | 52980 (250h) | 597 | 7665 | 52943
Deck Air Compressor |  | 0 | 0 | NA | 0 |  |  | 0 | NA | 0
Run hrs for bow thruster 1 |  | 14 | 268 | 2201 | 8299 |  |  | 254 | 2187 | 8285
Run hrs for bow thruster 2 |  | 14 | 268 | 2206 | 8293 |  |  | 254 | 2192 | 8279
Run hrs for stern thruster |  | 14 | 268 | 2167 | 8257 |  |  | 254 | 2153 | 8243
Run hrs for Main towing winch |  | 0 | 18 | 164 | 1399 |  |  | 18 | 164 | 1399
Run hrs for crane |  | 0 | 11 | 373 | 810 |  |  | 11 | 373 | 810
PASSENGER
Personnel |  |  | Personnel management |  | COMMENTS
Name | Company | Position | ARRIVAL DATE | DEPARTURE DATE
Lepinda Buchycka Hanyfa | Vaalco |  | 2026-06-25 | 2026-06-26
Manfoumbi Audrey G | Vaalco |  | 2026-06-25 | 2026-06-26
Dianga Koumba Eddy Lens | Vaalco |  | 2026-06-25 | 2026-06-26
Letadi Makoki Landry | Vaalco |  | 2026-06-25 | 2026-06-26
Mounguengui Jean Yves | Vaalco |  | 2026-06-25 | 2026-06-26
HSE
Categories | To date | Today | TOTAL | COMMENTS
PTW : Permit to work | 0 | 0 | 0
Tool Box Meetings | 639 | 4 | 643
Drills | 49 | 0 | 49
Risk Assessments/JSA's | 13 | 0 | 13
Workdays lost | 0 | 0 | 0
PD : Property Damage | 0 | 0 | 0
Near Misses | 7 | 0 | 7
Medical Reports | 0 | 0 | 0
Activity last 24H:
START | FINISH | DURATION | OPERATION
0:00 | 5:35 | 5:35 | VSL Steaming at oil field
5:35 | 6:15 | 0:40 | DP Mode. ETAME pax tx.
6:15 | 6:35 | 0:20 | DP Mode. Joystick transit to FSO Teli.
6:35 | 8:00 | 1:25 | DP Mode. Stby out 500 m zone , instruction from FSO Teli.
8:00 | 11:45 | 3:45 | DP Mode. Cargo ops., FSO Teli.
11:45 | 12:45 | 1:00 | VSL uw to SEENT
12:45 | 14:10 | 1:25 | DP Mode. SEENT platform. Stby out 500 m zone .
14:10 | 14:30 | 0:20 | VSL uw to ETAME platform.
14:30 | 16:45 | 2:15 | DP Mode. ETAME platform.
16:45 | 17:30 | 0:45 | VSL uw to SEENT
17:30 | 21:55 | 4:25 | DP Mode. SEENT platform. Cargo ops. Bunkering FW
21:55 | 23:59 | 2:04 | VSL Steaming at oil field

## Technical Info
TECHNICAL INFO
M/E No1 | [12 empty] | M/E No2
Engine RPM |  | Engine load [kw[%]] |  |  | Prop. Pitch [%] |  |  | Sumptank [lt] |  |  |  |  | Engine RPM |  | Engine load [kw[%]] |  |  | Prop. Pitch [%] |  |  | Sumptank [lt]
980 |  | 50 |  |  | 50 |  |  | 1000 |  |  |  |  | 982 |  | 50 |  |  | 50 |  |  | 1000
Exhaust gas temp [*C] | [12 empty] | Exhaust gas temp [*C]
NoΑ1 | NoΑ2 | NoΑ3 | NoΑ4 | NoΑ5 | NoΑ6 | NoΒ1 | NoΒ2 | NoΒ3 | NoΒ4 | NoΒ5 | NoΒ6 | Deviation | NoΑ1 | NoΑ2 | NoΑ3 | NoΑ4 | NoΑ5 | NoΑ6 | NoΒ1 | NoΒ2 | NoΒ3 | NoΒ4 | NoΒ5 | NoΒ6 | Deviation
320 | 319 | 317 | 325 | 320 | 328 | 330 | 320 | 319 | 319 | 317 | 320 | 15 | 318 | 325 | 330 | 335 | 319 | 317 | 319 | 320 | 325 | 330 | 318 | 320 | 20
Exhaust gas temp [*C] NoΑ1: T/C No1; Exhaust gas temp [*C] NoΒ1: T/C No2 |  | T/C No1 | [5 empty] | T/C No2
Exhaust gas temp [*C] NoΑ1: Exhaust gas Temp (Before / After) [*C]; Exhaust gas temp [*C] NoΒ1: Exhaust gas Temp (Before / After) [*C] |  | Exhaust gas Temp (Before / After) [*C] | [5 empty] | Exhaust gas Temp (Before / After) [*C]
Exhaust gas temp [*C] NoΑ1: 420; Exhaust gas temp [*C] NoΑ2: 380; Exhaust gas temp [*C] NoΒ1: 425; Exhaust gas temp [*C] NoΒ2: 385 |  | 418 | 382 |  |  |  |  | 419 | 380
Exhaust gas temp [*C] NoΑ1: RPM; Exhaust gas temp [*C] NoΒ1: RPM |  | RPM | [5 empty] | RPM
Exhaust gas temp [*C] NoΑ1: 9800; Exhaust gas temp [*C] NoΒ1: 9850 |  | 9900 | [5 empty] | 9850
Exhaust gas temp [*C] NoΑ1: Scav Pressure (Before / After Cooler) [bar]; Exhaust gas temp [*C] NoΑ6: ΔP |  | Scav Pressure (Before / After Cooler) [bar] |  |  |  |  | ΔP
Exhaust gas temp [*C] NoΑ1: N/A; Exhaust gas temp [*C] NoΑ2: 0.01; Exhaust gas temp [*C] NoΑ6: 0 bar |  | N/A | 0.01 |  |  |  | 0 bar
Exhaust gas temp [*C] NoΑ1: LO Pressure [bar]; Exhaust gas temp [*C] NoΒ1: FO Pressure [bar] |  | LO Pressure [bar] | [5 empty] | FO Pressure [bar]
Exhaust gas temp [*C] NoΑ1: 5; Exhaust gas temp [*C] NoΒ1: 8 |  | 5 | [5 empty] | 8
Exhaust gas temp [*C] NoΑ1: HT Temp [*C] (Before / After Cooler); Exhaust gas temp [*C] NoΒ1: HT Pressure [bar] (Before / After Cooler) |  | HT Temp [*C] (Before / After Cooler) | [5 empty] | HT Pressure [bar] (Before / After Cooler)
Exhaust gas temp [*C] NoΑ1: 85; Exhaust gas temp [*C] NoΑ2: 82; Exhaust gas temp [*C] NoΒ1: 4; Exhaust gas temp [*C] NoΒ2: 4.5 |  | 86 | 82 |  |  |  |  | 4 | 4.2
Exhaust gas temp [*C] NoΑ1: SW Temp [*C] (Before / After Cooler); Exhaust gas temp [*C] NoΒ1: SW Pressure [bar] (Before / After Cooler) |  | SW Temp [*C] (Before / After Cooler) | [5 empty] | SW Pressure [bar] (Before / After Cooler)
Exhaust gas temp [*C] NoΑ1: 32; Exhaust gas temp [*C] NoΑ2: 34; Exhaust gas temp [*C] NoΒ1: 48; Exhaust gas temp [*C] NoΒ2: 50 |  | 32 | 35 |  |  |  |  | 49 | 50
Exhaust gas temp [*C] NoΑ1: DG No1 |  | DG No2
Exhaust gas temp [*C] NoΑ1: Exhaust gas temp [*C] |  | Exhaust gas temp [*C]
No1 | No2 | No3 | No4 | No5 | No6 | No7 | No8 | No9 | No10 | No11 | No12 | Deviation | No1 | No2 | No3 | No4 | No5 | No6 | No7 | No8 | No9 | No10 | No11 | No12 | Deviation
Exhaust gas temp [*C] No7: N/A; Exhaust gas temp [*C] No8: N/A; Exhaust gas temp [*C] No9: N/A; Exhaust gas temp [*C] No10: N/A; Exhaust gas temp [*C] No11: N/A; Exhaust gas temp [*C] No12: N/A | C | 339 | 345 | 339 | 331 | 336 | 341 | N/A | N/A | N/A | N/A | N/A | N/A | 20*C
Exhaust gas temp [*C] No1: Alternator; Exhaust gas temp [*C] No7: T/C |  | Alternator | [5 empty] | T/C
Exhaust gas temp [*C] No1: Fwd Bearing temp; Exhaust gas temp [*C] No3: Aft Bearing temp; Exhaust gas temp [*C] No7: Exhaust gas Temp (Before / After) [*C] |  | Fwd Bearing temp |  | Aft Bearing temp |  |  |  | Exhaust gas Temp (Before / After) [*C]
[13 empty] | 46 |  | 45 |  |  |  | 410 | 315 | bar: Exhaust gas temp [*C] No2; Exhaust gas temp [*C] No4 to Exhaust gas temp [*C] No6; Exhaust gas temp [*C] No9 to Exhaust gas temp [*C] No12
Exhaust gas temp [*C] No1: N/A |  | S/G No1 |  |  |  |  | S/G No2
Exhaust gas temp [*C] No1: Exhaust gas temp [*C] |  | Fwd Bearing temp |  | Aft Bearing temp |  |  | Fwd Bearing temp |  | Aft Bearing temp
No1 | No2 | No3 | No4 | No5 | No6 | No7 | No8 | No9 | No10 | No11 | No12 | Deviation | 44 |  | 46 |  |  | 44 |  | 47
N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 *C | N/A |  | N/A |  |  | N/A |  | N/A
Alternator
Fwd Bearing temp |  | Aft Bearing temp
N/A |  | N/A
Intermediate Bearings Temperature
Port side Forward |  | 40 |  | Starboard side Forward |  |  | 40
Port side Aft |  | 39 |  | Starboard side Aft |  |  | 38

## HSE Statistics
| HSE Statistics | [16 empty] | Month | [6 empty] | June
Days
S/N | Indicators | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Total | Remarks
1 | POB (Personnel onboard) | 16 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
2 | Man - Hours | 192 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | [5 empty] | 4692
3 | Near misses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1
4 | Incidents - Accidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
5 | FAC (First Aid Cases) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
6 | MTC (Medical Treatment Cases) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
7 | LTI (Lost Time Injury) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
8 | RWDC (Restricted Work Day Cases) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
9 | PTW (Permit To Work) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
10 | Daily tool box talks | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [5 empty] | 104
11 | Training Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
12 | Safety Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
13 | Safety Observation Cards ( SOC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
14 | Audit/Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
Explanation:
Man Hours is POB x working hours per POB
First Aid Case (FAC) This is any one-time treatment and subsequent observation or minor injuries such as C28 D25 cuts, burns, splinters, etc.
Medical Treatment Case (MTC) Any work related injury that involves neither lost workdays nor restricted workdays but which requires treatment by a physician or other medical specialist.
LTI (Lost Time Injury) A workplace injury is only considered an LTI if the worker is unable to perform their regular duties, takes time off to recover or is assigned to modified tasks while they heal.
Restricted work day case (RWDC) Any work-related injury other than a fatality or lost work day case which results in a person being unfit for full performance of the regular job on any day after the occupational injury.